## Slide 1: How to Use This Template
This slide deck was developed as a guided template to help countries prepare their own investment case for a Sample Registration System (SRS).
Please replace all placeholder text (e.g., [COUNTRY], example figures, sample narratives) with your country-specific content.
You may adapt, add, or remove slides to reflect your national context, priorities, and available data.
Suggested examples, references, and visuals are included , please update them with your own data and sources.
The acknowledgment slide is included at the end; please keep or adapt it as appropriate.

## Slide 2: A Business Case for a Sample Registration System (SRS)
[COUNTRY]

## Slide 3: Purpose, and Scope

## Slide 4: Problem statement
Purpose: Establish urgency and context Include:
Data gaps (timeliness, completeness, cause-of-death coverage, subnational detail) Why existing methods (census, household surveys, models) are insufficient
Consequences for policy-making, epidemic response, SDG monitoring
If possible, add a visual (chart, map, or graphic showing gaps)
Resources/Examples:
[1] Raja MHR, Hoodbhoy Z, Sheikh S, Nisar MI, Soofi SB, Siddiqi S, Mirza Z, Bashir F, Mehmood MT, Samad Z. A systems-change approach to addressing the mortality surveillance gap in Pakistan. J Glob Health. 2025 Aug 4;15:03027. doi: 10.7189/jogh.15.03027. PMID: 40755021; PMCID: PMC12319398.

## Slide 5: Purpose and vision
Purpose: Link the SRS to broader national goals Include:
Purpose statement: e.g., “Enable government to continuously produce reliable mortality and cause-of-death data”
Vision: data-driven decision-making, health security, CRVS improvement
Alignment with national development plans, health strategies, and global commitments (SDGs, UHC, health security frameworks)
List scope items clearly: births, deaths, causes of death, etc.
State expected geographic coverage and level of representativeness.
*Refer to the SRS implementation vision developed in the situational assessment report.

## Slide 6: What is an SRS?
Purpose: Explain the concept simply
Include:
Definition of SRS Core functions: notification & registration, cause-of-death assignment, integration with CRVS
Simple diagram showing data flow from community to national level
How it complements existing systems
Resources/Examples:
[2] Amouzou, A., Aveika, A., Van Dyk, F., Kante, M., Koffi, A., Rahman, H., Williams, E., Wilson, E., & Zack, K. (2025). Planning, implementing and sustaining a sample mortality surveillance system: 12 steps [Technical document in preparation, not publicly available]. Bill & Melinda Gates Foundation / COMSA Mozambique.

## Slide 7: SRS is feasible … and Leads to Action
Three SRS systems in Africa
  Sierra Leone (2018 – present)
  Mozambique (2018 – present)
  Tanzania (1992 – 2004)
Sample use cases:
  Sierra Leone: Uncovered significant, previously undetected malaria mortality in adults. Led to deeper investigation, triangulation with other data sources, and influencing current policy discussions. Other findings led WHO to revise estimate of maternal mortality downward for Sierra Leone [3].
  Mozambique: Fully integrated into government systems in 2022. Most recent data currently being fed into regional policy and planning process.
  Tanzania: Uncovered huge burden of child malaria mortality occurring at home after treatment; district reallocated annual budget to establish bed net revolving fund; government changed first-line malaria drug [4]. Data also used to develop national NCD policy [5]

## Slide 8: Comparative advantage
Purpose: Show why SRS is better than alternatives Include:
Limitations of current data sources (timeliness, representativeness, cost)
Unique value of SRS (cause-of-death detail, continuous data, actionable at subnational level)
How it integrates with CRVS, disease surveillance, and national statistics
Differential cost of measuring SDG indicators with SRS vs alternatives
Resources/Examples:
[6] Revenga, R., & Muñoz, D. C. (2021). Development of an economic case for civil registration and vital statistics: Final technical report [Technical report]. International Development Research Centre (IDRC). https://idl-bnc-idrc.dspacedirect.org/items/ad5be68e-7beb-43e6-b4b5-3d08ea108035

## Slide 9: [EXAMPLE] Existing Alternatives do not Meet the Need [7]
System | Representativeness | Sustainability | Timeliness | Mortality | Tradeoffs
National Census | Entire population High completeness | High | Once per decade | Total & maternal mortality No cause of death | Inadequate timeliness No cause of death
Surveys (e.g., DHS, MICS) | National level Regional level for some indicators High for sample clusters | Medium | Five years | Maternal and child mortality Specific causes only with addition of verbal autopsy module | Sample sizes usually too small to obtain cause data Not timely
Health and Demographic Surveillance | Not representative High for surveillance site | Medium | Varies | Varies | Not representative
CRVS | Entire population Birth registration high (>80%) Death registration low (<30%) | High | Currently no routinely produced statistical outputs | Only for facility deaths | Low completeness Timeliness Biased cause of death data
SRS | National and subnational levels High for sampled/model areas | High | Continuous, near time | Total and cause-specific mortality | Requires establishment & maintenance of sample sites
List current alternatives (household surveys, census, modelled estimates).
Highlight their weaknesses: infrequent, not representative, lack cause-of-death.
Conclude with why SRS fills the gap uniquely.
[7] Setel, P., Weiss, W., & Kwarah, W. (2023, October). A business case for a sample registration system (SRS) in Ghana [Slides presentation]. USAID; Data for Impact/Vital Strategies.

## Slide 10: [EXAMPLE] Comparative Costs [7]
System | Annualized Cost | Five-year Cost | Ten-year Cost | Comment
National Population and Housing Census | $4.5m |  | $45.5 | From government allocation for NPHC 2021
Demographic and Health Survey | $1m | $5m | $10m | USAID Contribution
Health and Demographic Surveillance Sites | Varies | Varies | Varies | Varies by site size and field methodology
Civil Registration and Vital Statistics System | $1.1m | $5.5m | $11m | From government appropriation bill
Sample Mortality Surveillance System | $0.78m - 1.1m | $3.9 - $5.5m | $7.8 - $11m | [2,5]
[7] Setel, P., Weiss, W., & Kwarah, W. (2023, October). A business case for a sample registration system (SRS) in Ghana [Slides presentation]. USAID; Data for Impact/Vital Strategies.

## Slide 11: SRS design
Solution

## Slide 12: A Well-Functioning SRS delivers on the Pillars of Success
Provides continuous source of crucial mortality burden data to prioritize, design, implement, and monitor scaled health and social policies
Builds culture of collection and use of Ghana’s own high quality mortality data
May enable detection and provides platform for deeper investigation and response to nearby outbreaks
Total/Excess mortality measurement under pandemic conditions
Platform for integrated disease surveillance
Opportunity to develop, implement and ultimately scale optimal vital event notification & registration practices to achieve universal registration
Creates in-country management and technical capacity
Pillar 1
Data-driven decision-making
Pillar 2
Contributing to Health Security
Pillar 3
CRVS Improvement
Primary Benefits
Secondary Benefits
Population denominators
Tracking of health-related SDGs
1 Adapted from [8]
[7] Setel, P., Weiss, W., & Kwarah, W. (2023, October). A business case for a sample registration system (SRS) in Ghana [Slides presentation]. USAID; Data for Impact/Vital Strategies.
Cost savings by dropping mortality modules from household surveys
Provides development partners and the global health community with accurate, current measures of core population health indicators

## Slide 13: Instructions
For each pillar (Data-driven decisions, Health security, CRVS improvement), include:
A short definition.
One visual/data example (or hypothetical local scenario).
Relevance to national context.
Below you can find examples

## Slide 14: Accurate sub-national mortality data allows for targeted prioritization
[EXAMPLE] Pillar 1: Data-Driven Decision-Making
Chart: 
| National
Malaria | 19998.6938
Diarrheal | 14997.242
Lower respiratory | 20030.445
Preterm birth | 12167.0963
Birth asphyxia | 18333.8155
Neonatal infection | 12561.0617
Chart: 
| National | National (future) | Ashanti | Brong-Ahafo | Central | Eastern | Greater Accra | Northern | Upper East | Upper West | Volta | Western | Western North | Oti | Ahafo | Bono | Bono East | Savannah
HIV/AIDS | 19998.6938 | 5601.0906 | 5040.9815 | 1988.3871 | 5601.0906 | 812.1581 | 1792.349 | 3640.7089 | 280.0545 | 128.8251 | 336.0654 | 140.0273 | 238.0463 | 1792.349 | 3640.7089 | 336.0654 | 140.0273 | 1988.3871
Diarrheal | 14997.242 | 4234.9666 | 5618.5178 | 3967.7495 | 4234.9666 | 311.9705 | 178.3982 | 177.4016 | 198.916 | 146.1818 | 72.5135 | 27.4442 | 63.1822 | 178.3982 | 177.4016 | 72.5135 | 27.4442 | 3967.7495
Lower respiratory | 20030.445 | 5415.351 | 9490.4604 | 4064.6889 | 5415.351 | 290.7665 | 235.4619 | 145.9098 | 198.623 | 83.1963 | 48.6934 | 5.6229 | 51.6708 | 235.4619 | 145.9098 | 48.6934 | 5.6229 | 4064.6889
Preterm birth | 12167.0963 | 2721.3925 | 4723.9394 | 2382.1167 | 2721.3925 | 1339.754 | 418.2039 | 73.0607 | 285.9997 | 114.1974 | 37.1695 | 32.6934 | 38.569 | 418.2039 | 73.0607 | 37.1695 | 32.6934 | 2382.1167
Birth asphyxia | 18333.8155 | 4100.6915 | 7118.2007 | 3589.4585 | 4100.6915 | 2018.7892 | 630.1646 | 110.0904 | 430.9546 | 172.0768 | 56.0084 | 49.2636 | 58.1172 | 630.1646 | 110.0904 | 56.0084 | 49.2636 | 3589.4585
Neonatal infection | 12561.0617 | 2809.51 | 4876.8986 | 2459.2486 | 2809.51 | 1383.1347 | 431.7452 | 75.4263 | 295.2603 | 117.8951 | 38.3731 | 33.752 | 39.8179 | 431.7452 | 75.4263 | 38.3731 | 33.752 | 2459.2486
Current state Under 5 Causes of Death2
Hypothetical future scenario with SRS Data
Low completion of national death registration data contributes to inaccurate aggregate estimates
National estimates derived from models (e.g., GBD) and lack credibility
Infrequent survey cycles result in outdated estimates
With SRS, national data measures COD distribution
Accurate sub-national COD burden available and regularly updated, permitting analysis of trends
Diarrheal diseases
Malaria
Lower resp infections
Preterm birth
Birth asphyxia
Neonatal infections

## Slide 15: [Mozambique example]
Provides proportional cause of death data for all age groups
Demonstrates to Networks/MOH need for tiered services: acute and episodic care for under 5s (infections), long-term care and management for adults (CVD; Cancer)
Cause of death fraction (%) by age Group - COMSA Data 2019-2020 [9]

## Slide 16: Pillar 2: Contributing to Health Security
Contribution | Current Status | Case or Potential Benefit
Contributing to early outbreak detection, investigation and response | No routine system capable of detecting outbreaks of known epidemic-prone or new, fatal diseases | Prepared and trained teams of verbal autopsy interviewers and supervisors can be mobilized as part of outbreak detection and response effort
Timely measurement of excess mortality during a pandemic | Limited, un-sustained success implementing rapid mortality surveillance – hospitals only. No timely source of community mortality | Direct measurement of excess mortality due to pandemics
Integrated Collaborative Surveillance | Siloed surveillance, no mortality surveillance | Contributes to Health Security and MOH-led use of multiple surveillance system outputs for comprehensive approach to early detection, response and impact measurement
[7] Setel, P., Weiss, W., & Kwarah, W. (2023, October). A business case for a sample registration system (SRS) in Ghana [Slides presentation]. USAID; Data for Impact/Vital Strategies.

## Slide 17: Pillar 3: CRVS Learning and Improvement
Function | Current Status | Opportunities for Improvement through SRS
Death notification and registration (BDR) | Low completeness | Design and implement sustainable, scalable active death notification for eventual national expansion
Causes of death in population (MOH) | Cause of death available only at facilities; 70-80% mortality occurs elsewhere | Develop complete picture of leading causes of death by age group and sex through application of verbal autopsy; strengthened cause of death certification at health facilities
[7] Setel, P., Weiss, W., & Kwarah, W. (2023, October). A business case for a sample registration system (SRS) in Ghana [Slides presentation]. USAID; Data for Impact/Vital Strategies.

## Slide 18: Benefits and Return of Investment
Purpose: Sell the value proposition Include:
Primary benefits: evidence-based planning, outbreak detection, improved CRVS operations, Data Accuracy and Consistency
Economic benefits:
Social benefits: equity, better targeting of services, accountability…
Resources/Examples:
[6] Revenga, R., & Muñoz, D. C. (2021). Development of an economic case for civil registration and vital statistics: Final technical report [Technical report]. International Development Research Centre (IDRC). https://idl-bnc-idrc.dspacedirect.org/items/ad5be68e-7beb-43e6-b4b5-3d08ea108035
[10] Espey, J. (2019). The costs and benefits of CRVS as a tool for women’s empowerment (Brief 1, Paper 4). Knowledge Brief Series on Gender and CRVS. Centre of Excellence for Civil Registration and Vital Statistics Systems, International Development Research Centre; Open Data Watch. https://opendatawatch.com/wp-content/uploads/KnowlegeBriefs/CRVS-Brief-1-EN.pdf

## Slide 19: Beneficiaries and Benefits of an SRS
Purpose: Show who gains from an SRS and how it delivers value to different stakeholders
Include:
List of the main beneficiaries of the SRS in your country (refer to the interest–power grid).
Describe the specific benefits each beneficiary will gain from the system.

## Slide 20: Costs and Cost Drivers
Briefly describe the estimated costs according to your Costed action plan

## Slide 21: Risk Assessment

## Slide 22: Risk assessment
Operational Risk
Mitigation strategy:
Technical Risk
Mitigation strategy:
Financial Risk
Mitigation strategy:
Briefly describe a list of identified risks in different categories and your proposed mitigation strategy

## Slide 23: Implementation Plan

## Slide 24: Timeline
Include 4 years plan Gantt chart

## Slide 25: Conclusion

## Slide 26: Way forward
Summary:
Next steps:

## Slide 27: References cited
[1] Raja MHR, Hoodbhoy Z, Sheikh S, Nisar MI, Soofi SB, Siddiqi S, Mirza Z, Bashir F, Mehmood MT, Samad Z. A systems-change approach to addressing the mortality surveillance gap in Pakistan. J Glob Health. 2025 Aug 4;15:03027. doi: 10.7189/jogh.15.03027. PMID: 40755021; PMCID: PMC12319398.
[2] Amouzou, A., Aveika, A., Van Dyk, F., Kante, M., Koffi, A., Rahman, H., Williams, E., Wilson, E., & Zack, K. (2025). Planning, implementing and sustaining a sample mortality surveillance system: 12 steps [Technical document in preparation, not publicly available]. Bill & Melinda Gates Foundation / COMSA Mozambique.
[3] Ronald Carshon, Marsh, Rashid Ansumana, Amara Jambai, Ibrahim Bob Swaray, et. al. on behalf of the HEAL SL Team. (2023) “Healthy Sierra Leone (HEAL-SL): Causes of death in Sierra Leone 2018 - 2022: Lessons learned” LEAPS CONVENING (Learning, Expanding and Adapting Public Health Surveillance: Leveraging Sampling-Based Platforms), June 19, 2023
[4] de Savigny, D., Setel, P. Whiting, D., Kasale, H. et al. (undated) “Linking Demographic Surveillance and Health Service Needs: The AMMP/TEHIP Experience in Morogoro, Tanzania.” Ministry of Health, The Policy Implications of Adult Morbidity and Mortality Project (AMMP), and Tanzania Essential Health Intervention Project (TEHIP)
[5] Ministry of Health, United Republic of Tanzania (2004). “The Policy Implications of Tanzania’s Mortality Burden: a Ten-Year Community-Based Perspective. Ministry of Health, Dar es Salaam
[6] Revenga, R., & Muñoz, D. C. (2021). Development of an economic case for civil registration and vital statistics: Final technical report [Technical report]. International Development Research Centre (IDRC). https://idl-bnc-idrc.dspacedirect.org/items/ad5be68e-7beb-43e6-b4b5-3d08ea108035
[7] Setel, P., Weiss, W., & Kwarah, W. (2023, October). A business case for a sample registration system (SRS) in Ghana [Slides presentation]. USAID; Data for Impact/Vital Strategies.
[8] Anon. (2017) “A childhood mortality focused Enhanced Sample Registration System providing precision public health and continental vital statistics: Co-Funding Investment Case – Summary of Key Findings,” Bill and Melinda Gates Foundation, Seattle
[9] Mozambique Institute of Public Health/Ministry of Health
[10] Espey, J. (2019). The costs and benefits of CRVS as a tool for women’s empowerment (Brief 1, Paper 4). Knowledge Brief Series on Gender and CRVS. Centre of Excellence for Civil Registration and Vital Statistics Systems, International Development Research Centre; Open Data Watch. https://opendatawatch.com/wp-content/uploads/KnowlegeBriefs/CRVS-Brief-1-EN.pdf

## Slide 28: Acknowledgment
The development of this slide deck by Swiss TPH builds on and adapts materials mainly from two key resources: A business case for a sample registration system (SRS) in Ghana (Setel, Weiss, & Kwarah, 2023) and Development of an economic case for civil registration and vital statistics: Final technical report (Revenga & Muñoz, 2021). We gratefully acknowledge the authors and institutions behind these works for providing foundational content and inspiration.